## User stories
PROJECT | SNAKE GAME
Start | Week 8
End | Week 13
Owner | Your name and student ID
As a user, I want:
|  | No | User stories
|  | 1 | to create the snake game looks real game
|  | 2 | the game board looks like simple with black back ground colour
|  | 3 | to use arrows key to move
|  | 4 | read all the details
|  | 5 | to use ESC button through exit the game
|  | 6 | to use SPACE to run and hold the player
|  | 7 | to see apple in the game board
|  | 8 | game has 1 snack
|  | 9 | prey looks like emoji
|  | 10 | login to play the game with user name and password
|  | 11 | display the score
|  | 12 | snack looks like Green colour
|  | 13 | snack increase the lengh after eat prey
|  | 14 | when snack hit the border you will see game over
|  | 15 | after game over retry option available
|  | 16 | programmer name illustrated by lable
|  | 17 | snack speed is medium not fast not even slow
|  | 18 | size of game baord also looks perfect
19
20

## Snake-game
PROJECT | SNAKE GAME
Start | Week 8
End | Week 13
Developer | Your name and student ID
No | Level-1 tasks | Level-2 tasks | Level-3 tasks | Priority | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Note
1 | Create a repository for the project on GitHub |  |  | 1 | 100%
2 | Create and update product backlog |  |  | 1 | 100%
3 | Build the snake game as in the product backlog |  |  | 2
3.1 |  | Build the GUI
3.1.1 |  |  | GUI for gameboard
3.1.2 |  |  | GUI for login form |  |  | 50% |  |  | 50%
GUI for the playing snake and prey
GUI for scores
3.2 |  | Build the game logic |  |  |  | 50% |  | 50%
3.2.1 |  |  | Snake logic | [5 empty] | 100%
|  |  | Prey Logic |  |  |  | 50% |  | 50%
|  |  | Game Over Logic |  |  | 10% | 30% | 30% | 30%
|  |  | Login Logic |  | 30% | 30% |  | 40%
|  |  | Score Logic |  |  |  | 100%
4 | Test and deploy the game |  |  | 3 | [5 empty] | 100%
|  | Login Test | [7 empty] | 100%
|  | Snake movement test | [7 empty] | 100%
|  | Snake eating Prey test | [7 empty] | 100%
|  | Changing Score test | [7 empty] | 100%
|  | Game Over test | [5 empty] | 20% | 80%
5 | Document the game |  |  | 4 | [5 empty] | 100%
|  | Making YouTube Video | [7 empty] | 100%
|  | Instruction to how to play | [7 empty] | 100%
| YOU TUBE LINK | https://youtu.be/QlCh7wBPLr4